## Plan Items
S |  |  | M |  |  |  |  | A | R | T
Specific - Target a specific area of Improvement. |  |  | Measurable - Quantify or at least suggest an indicator of progress. |  |  |  |  | Achievable, Accountable, Assignable - Can it be done and if so, be specific who will do it. | Relevant - State the goal to be achieved making sure it's relevant to the individual and the organization. | Time Bound - specify when the result(s) can be achieved.
Order | Level | Title | Metric | Metric Rollup | Baseline | Target | Current Value | Assigned To | Description | Status | Start | Due | Update Frequency
1 | Overarching Goal | Accept and serve more students with unique learning needs in our school. | Enrollment Numbers |  | 2 | 8 | 2 | erin.brown@Catholicforus.com | Part of our mission as a school to serve all. | On Track | 2018-10-15 | 2020-09-01 | Yearly
1.1 | Milestones | Hire certified special education and related services staff | [6 empty] | 10-20% of all school populations have a need beyond what general education staff can provide
1.1.1 | Projects | Hire and retain a part time Occupational Therapist | Budget | Manual | 2000 | 130000 | 5000 | erin.brown@Catholicforus.com | Anticipated growth of 10% more students served within the school. | On Track | 2018-10-15 | 2020-09-01 | Yearly
1.1.1.1 | Tactics | Create plan with Advisory Council about adding to budget and future fundraisers | Fundraisers |  | 50 | 35000 | 5000 | erin.brown@Catholicforus.com | Fundraising is needed to retain position after EMBRACE Grant | At Risk | 2017-09-01 | 2018-05-04 | Yearly
1.1.2 | Projects | Determine what students need these services. | SIT and GEI process |  | 2% of i | 80% of identified | 5% of i | justin.edwards@teachers.com | Identifying areas of weakness in current curriculum or instruction. | On Track | 2018-02-01 | 2018-05-01 | Monthly
1.1.2.1 | Tactics | Students identified by Teacher/Parent/District. | The Screener of Handwriting Proficiency |  | 0 | 10 | 1 | justin.edwards@teachers.com | Part of school SIT process and district GEI process | On Track | 2017-09-01 | 2018-09-01 | Monthly
1.1.2.2 | Tactics | Students newly identified by Occupational Therapist | School Functional Assessment |  | 0% | 20% | 5% | mark.dunstin@Catholicforus.com | Assist with getting early intervention | At Risk | 2018-10-15 | 2019-05-20 | Monthly
1.2 | Milestones | Provide teacher professional development |  | Manual
1.2.1 | Projects | Scehdule four training sessions for teachers on sensory needs | Surveys |  | Satisfactory | Exemplary | Satisfactory | erin.brown@Catholicforus.com | Teacher professional development with follow-up instruction is the number one factor in quality instructional practices | Achieved | 2017-09-01 | 2018-05-01 | Quarterly
1.2.2 | Projects | Follow-up three times a year to determine | Fill out lesson plan using new skill |  | 0 lessons | 1 a month | 0 a month | principal@teach.com | Professional development is only successful when followed up by check ins to ensure skills are used effectively | At Risk | 2017-09-01 | 2018-05-20 | 3x a year
1.3 | Milestones | Foster an inclusive environment
1.3.1 | Projects | Provide open house to parish families with talk on special services provided and why they are provided | Attendees |  | 0 | 20 | 0 | erin.brown@Catholicforus.com | Provides awareness on inclusion opportunities within the school and allows parish school connection. | On Track | 2018-10-12 | 2019-04-12 | Yearly
1.3.2 | Projects | Provide daily time for special education professionals to assist in classrooms | Schedules of In-Class Inclusion Time |  | 0 hrs a day | 4 hrs a day | 1 hr a day | principal@teach.com | Students learn best when with peers and not missing classroom instruction | At Risk | 2018-09-15 | 2019-04-15 | Yearly
1.4 | Milestones | Provide direct service in the classroom if possible and pull-out only when required
1.4 | Projects | 30 Students in K through 2nd grade need small group instruction in fine motor and handwriting | The Screener of Handwriting Proficiency |  | Below Level | At Level | Below Level | justin.edwards@teachers.com | Whole group instruction and in-class interventions have been exhausted | On Track | 2018-09-15 | 2019-04-15 | Monthly
1.5 | Projects | 30% of students scoring below average in pragmatic language will improve into the average range | TOPL-2 |  | Below Level | At Level | Below Level | kelly@teachall.com | Pragmatic language can effect social skills and classroom behavior | On Track | 2018-09-15 | 2019-04-15 | Monthly
1.5.1 | Tactics | All students referred by classroom teachers will be assessed in pragmatic language. | TOPL-2 |  | Below Level | At Level | Below Level | kelly@teachall.com | Pragmatic language can effect social skills and classroom behavior | On Track | 2018-09-15 | 2019-04-15 | Monthly
1.5.2 | Tactics | Students will receive intervention in Small Group using Superflex and Michelle Garcia Winner's Interoception Curriculum | Schedules |  | 0 days | 2 days a week | 1 day a month | kelly@teachall.com | Superflex and Interoception have success in the target population on building this skill. | On Track | 2018-10-01 | 2018-04-10 | Weekly